## Slide 1: RoboTour A robot that improves your experience in museums
Notes: Finn
This is RoboTour. RoboTour is a multi-purpose assistive robot tailored to museum visitors. Our mission is to provide a dynamic cultural experience for museum visitors through 2 unique value propositions:
Robot guiding assistance, for example, RoboTour take me to the newest painting. Where is the Picasso painting. Take me to the toilet?
Elimination of language barriers, RoboTour is a walking tour-guide which provides multi-language support. RoboTour will take you to the exhibitions that you want to see and in your primary language.
As outlined in our project plan, we have achieved 4 key milestones for demo 1: Basic Robot Building, App-to-Robot Communication, Basic UI Designs, and Basic Collision Avoidance.
For each of these milestone, our members will also talk about what’s next steps.

## Slide 2: Recap of Demo 1
App-to-Robot Communication
Basic Robot Building

## Slide 3: Recap of Demo 1
Basic Collision Avoidance
Completed Basic User Interface
Client Demo 1:
Stop when detects obstacles
Only apply at going forward
Using multithreading

## Slide 4: Following line path
The robot can navigate simple branching line paths so that it reaches a predetermined destination.

## Slide 5: Basic Speech Commands
The user can interact with the robot through the app via English speech. The user can send basic commands to the robot e.g. “Take me to X”.

## Slide 6: Dynamic collision avoidance and navigation

## Slide 7: Motorised Robot Pointer
When RoboTour reaches an art piece, it points points to it.

## Slide 8: Resources/Member
Time Spent: 68 Remain: 132 (hrs/member)
Guest lectures: 3 (of 6)
Demonstrations 1 (of 4)
Group meetings: 11 (of 25)
Planning and Admin 16 (of 40)
Debugging & Testing: 10 (of 30)
Code Reviews: 2 (of 10)
Robot construction: 5 (of 10)
Code development 20 (of 75)
Money Spent: £23.43 Remain: £176.57
Microcontroller (ATMEGA88A-AU) £2.50
Sensor (KTIR 0711S) £0.00
Sensor (QRE1113GR) £5.64
Crystal (MCRS020000F1) £0.29
Line sensor (Technician Time) £15
Fig 13: Budget pie chart
Notes: Michal
Main:
Conclusion: We are on schedule to completing tasks because it took us 50 hours/member of work each to get to this point

## Slide 9: Plans Going Forward - Revised Gantt Chart
Fig 11: Gantt chart
Notes: - Mariyana still ill and not in Edinburgh - We expected her to be back, but due to medical complications she hasn’t come back yet- hence we need to reshuffle
- We also reshuffled further according to each team members strengths
- We have done this to ensure that we we optimally use our time to produce the best quality work in an efficient manour.

## Slide 10: Live Demonstration
Notes: David

## Slide 11: Next Steps
Fig 12: Milestones for next client demo
Technical Achievement | Evidence
Speed Adjustment / Variable Speed | The robot is able to adjust the speed to the users’ requirements. Additionally, the robot stops if the connection drops or upon the the users request.
Improved User Interface | Allows the user to ask the robot for recommendations via text or speech. There will be a script of acceptable speech commands.
Complex Path Planning | The robot considers multiple paths between selected points and selects the one that minimises travel time.
3.1.3 Client Demo 3 - 14/03/2018
Notes: Here we have what we plan to have completed for Demo 2.
Address 4 points
The only difference with this is like Michal said we are building a custom line sensor for this demo.

## Slide 12: Thank You
We would like to welcome any questions or suggestions that you may have.
Notes: We would all like to thank you for listening to our demonstration. We would like to invite you to have a look at our current system and would welcome any questions or suggestions you may have.