## Sheet1
|  |  | Alice | David | Deividas | Finn | Mahbub | Mariyana | Michal
Task | Expected man-hours | Assigned | 14 | 24 | 16 | 10 | 28 | 12 | 36
Constructing the drive base of the robot | 20 | 20 |  |  | 8 |  | 8 |  | 4
Developing line-following algorithm | 20 | 20 |  |  | 4 |  | 4 |  | 12
Designing line-sensor | 10 | 10 | [6 empty] | 10
Designing GUI | 12 | 12 |  | 8 |  |  | 4
Developing ev3-app communciations | 20 | 20 | 10 | 10
Developing speech processing interface | 8 | 8 |  | 2 |  | 6
Admin | 50 | 50 | 4 | 4 | 4 | 4 | 12 | 12 | 10
0
0